## Project Plan (Archive) (hidden)
| WAVE 1 | CHPCC (Boris) | Urology (Dan) | Nutrition (Boris) | WAVE 2 | ORL (Dan) | Audiology (Dan) | Speech (Boris) | Endocrinology/GeMs/OWL (Shannon) | Gynecology (Shannon) | Behavioral Health/Psychiatry (Travis) | Plastic Surgery (Dan) | Sleep Center (Shannon) | Vaccine Clinic/Travel Clinic (Travis)
Pre-Work | 6/24-6/28 |  |  |  | Readiness: 7/8-7/26 IT: 7/22-7/26
Identify operational leads and template managers per specialty grouping, ensure they have time to dedicate to this optimization wave |  | Complete | Complete | Complete |  | In Progress | Complete | In Progress | Complete | Complete | Complete | In Progress | Complete | Complete
Identify the Epic DEPs included within each specialty grouping |  | Complete | Complete | Complete |  | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
Identify blocks in use for each DEP/Specialty |  | Complete | Complete | Complete |  | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
Ensure EAD and template manager understand blocks/tags/visit types --Share education powerpoint --Schedule meeting to review |  | Complete | Complete | Complete |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
Compile list of known Jira tickets (operations) --Rank top 5 priorities |  | Not Started | Complete | Complete |  | Not started | Not started | Not started | Not started | Not started | In Progress | Not started | Not started | In Progress
Compile list of known Jira tickets (IT) --Classify as in our out of scope for being related to this project |  | Complete | Complete | Complete |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
Review blocks and make recommendation for keep/remove based on visit type outcomes in GPS |  | Complete | Complete | Complete |  | Not started | Not started | Not started | Not started | Not started | In Progress | Not started | Not started | In Progress
Ensure EAD and template manager are adhering to guiding principles in their use of blocks and open scheduling |  | In progress | Complete | Complete |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
Send outlook invitations for that specialties pre-work, first meeting, close out meeting, and stabilization meeting |  | Sent Meeting #1 | Sent Meeting #1 | Sent Meeting #1 |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
Meeting 1 -- 90 mins | 7/1-7/5 | 2024-07-03 | 2024-07-02 | 2024-07-01 | 8/5-8/9
Conduct first meetings with department |  | In Progress | Complete | Complete
Review of recommended plan from BCH IT (Epic led) --Proposed block and template changes --Proposed GPS/visit type changes NOTE: The department should already have an understanding of blocks and appropriate block usage per BCH guidelines |  | In Progress | In Progress | Complete
To send after meeting -- Finalized scope based on priority for the department of optimization items for the specialty group |  | Not started | Not started | Complete
Build (weeks 2-3) | 7/8-7/19 |  |  |  | 8/12-8/23
Update all templates with appropriate tags and removing unnecssary blocks
Update decision trees to drive to right visit type/tag combo
Complete build on scoped priority optimization items
Configure allowed blocks for those departments to limit what can be used
Test (weeks 3-4) | 7/15-7/26 |  |  |  | 8/19-8/30
QA through peer review/2nd testing (including MyChart)
Conduct validation session with template builder to reproduce most impactful scheduling scenarios in REL to ensure accuracy
Departmental leads develop communication plan on what's impacting their departmental administrative and clinical staff understand the impact
Department review and sign-off (week 4) | 7/22-7/26 |  |  |  | 8/26-8/30
Review adherence to the agreed upon plan
Small demo what major changes occurred
Review support expectations "post-live" -Timeline for specific resources -Jira ticket expectations
Go-live planning and timeline of new templates and decision tree into PRD
Departmental leads communicate to their department what changes have occurred so entire administrative and clinical staff understand the impact

## Sheet2
Summary - Percentage of Departments - Functionality Adoption.
| Feb | April
Auto-scheduler works (Dept) | 100% | 100%
Auto-scheduler works (PLP) | 78%
Fast Pass (Live in PRD) | 35% | 86%
Ticket Scheduling (Amb Ref) |  | 18%
Ticket Scheduling - Follow Up order |  | 74%
Open/Direct Scheduling |  | 46%

## Project Objectives_NLB Copy
|  |  | Template & Scheduling Optimization |  |  |  | Self Service Options through the Portal |  |  |  | Other Projects
|  |  | Auto-scheduler works for Dept | Auto-scheduler works for PLP | Fast Pass (Live in PRD) | Ticket Scheduling (Amb Ref | Ticket Scheduling - Follow Up order | Open/Direct Scheduling | Open Scheduling | Direct Scheduling | Outlook Integration | (PostWaveOpt) Resolved | (PostWaveOpt) Open | Fast Pass Status Notes | Ticket Scheduling Notes: Automatic or Manual, Target date for opportunities, next step for all others | Build notes | Build Status/Questions: | PRD DEP Specialty
Area |  | Wave
Nutrition | MM | 1 |  |  |  | A | A |  |  |  |  | 7 |  | FP: Live for consults and follow ups. Next: Ready to start automatic ticket scheduling. Very cooperative and looking forward to adopting more functionality. (Willing to pilot) | Automatic release for both Consults and Follow Ups | No build change |  | Nutrition
Urology | LK | 1 |  |  |  | M | M |  | RAA |  |  | 25 |  | FP: live for consults and follow ups. Next: Look at opportunities for automatic ticket scheduling. Live for manual release. | Live for Manual Release for Consults and Follow Ups. | No build change |  | Pediatric Urology
CHPCC | MM | 1 |  |  |  |  | M |  |  |  |  | 9 |  | FP: Live for well child follow ups right now. New patient intake is controlled and scheduled manually for newborns and other. | Approved to go live with manual release in CHPCC, WEY, and MEHC primary cares) | No build change |  | Primary Care
ORL | LK | 2 |  |  |  | M | A |  | RAA |  |  | 19 |  | FP: Live for consults and follow ups. Next: Refine the logic - if any future audiology exclude from Fast Pass offers, also future Speech/Feeding, or MBS. Exclude - Vestibular Balance Lab, Consult vestibular. | Live for Referral - Manual Release and Follow Up - Automatic Release | Allow consults + follow ups, MUST TEST, Kate meet with Jenna to verify test results | removed specialty exclusion - ONLY FOR 539, AND 753 | Pediatric Oto
Audiology | LK | 2 |  |  |  | M | A |  | RAA |  |  | 6 |  | FP: Live for consults and follow ups. Next: Refine the logic - if any future audiology exclude from Fast Pass offers, also future Speech/Feeding, or MBS. Exclude - Vestibular Balance Lab, Consult vestibular. | Live for Referral - Manual Release and Follow Up - Automatic Release | Allow consults + follow ups, MUST TEST, Kate meet with Jenna to verify test results. Enable for these PRCs only: ABR APD ASSISTED AUDIO BAHS-ASSISTED BAHS-AUDIO BAHS-CONSULT CI-ASSISTED CI-AUDIO CI-CONSULT DSTI HA-ASSISTED HA-AUDIO HA-CONSUL | removed specialty exclusion | Pediatric Audiology
Speech | LK | 2 |  |  |  | M | M/A |  | RAA |  |  | 1 |  | FP: Live for consults and follow ups. Next: Refine the logic - if any future audiology exclude from Fast Pass offers, also future Speech/Feeding, or MBS. Exclude - Vestibular Balance Lab, Consult vestibular. | Live for Referral - Manual Release - Pending Ambulatory to complete build for different specialty orders for follow up automation. | Allow consults + follow ups, MUST TEST, Kate meet with Jenna to verify test results | removed specialty exclusion, added 562/773/856/855 to opt in | Speech
Endocrinology/GeMs/OWL | MM | 2 |  |  |  |  | A |  |  |  |  | 6 |  | FP: Live for most consults and follow ups - some exceptions including GeMs for consults and some coordinated Diabetes visits. | Live with Manual release for follow ups. Met with them 5/7/25 - Pending Department to indicate when they want to go live with automation/if there's any additional questions (working w/Kimchi) | https://jiraprod.tch.harvard.edu/browse/ITHD-233150 | PRC 528/1368/1389/1388/606/1369/1435/299/1380/747/305/306 removed specialty exclusion, added prc/specialty exclusion | Pediatric Endo
Gynecology | LK | 2 |  |  |  |  | M |  |  |  |  | 2 |  | FP: Live for follow ups, opportunity for consults in the future. | Live with Manual release for follow ups. Unable to automate until there is more conversation to update their follow up order. (Ambulatory owned) | Allow for birth control refills | removed specialty exclusion, added 622 to fp opt in | Gynecology
Behavioral Health/Psychiatry | RH | 2 |  |  |  |  | M | [6 empty] | FP: Not live for consults due to strict intake process and sequencing. Potential for follow ups but not useful at the moment. | Unable to enable manual until update to follow up order (Ambulatory owned) | Allow for follow ups only. | removed specialty exclusion, added 762 to fp opt in | Pediatric Psych
Plastic Surgery | LK | 2 |  |  |  | M | M |  | RAA |  |  | 4 |  | FP: Live for New Plagio consults. No real need with the other RFVs because patients want a specific time. Not managing a large waitlist. Next: Explore ticket scheduling for new Plagio patients | Live for Manual Release for Consults and Follow Ups. Opportunity to automate Follow Ups pending Plastics getting comfortable with how follow up scheduling is working | https://jiraprod.tch.harvard.edu/browse/ITHD-230744 | PRC 1408 ONLY: removed specialty exclusion, added prc/specialty exclusion | Pediatric Plastic
Sleep Center | RH | 2 |  |  |  |  | M |  |  |  |  | 3 |  | FP: Open to consults. Next: Testing and providing results to department | Manual release for follow ups, potential for automation pending department comfort. | Meeting scheduled Wednesday |  | Sleep Medicine
Vaccine Clinic/Travel Clinic | MM | 2 | [9 empty] | 2 |  | FP: Still opportunity for simple visits, not a good use in Travel Clinic. | Workflow favors direct/open scheduling rather than tickets. | Messaged Erica for feedback |  | Family Medicine
Developmental Medicine | MM | 3 |  |  |  |  | A |  |  |  |  | 1 |  | FP: Live for follow ups. Next: Explore adding consults to Fast Pass | Live for Automatic Release for Follow Ups. | No build change |  | Pediatric Develop
ASAP | MM | 3 |  |  |  |  | M | [6 empty] | Approved for follow ups in Fast Pass except Social Work visits. Some operational clean up but want to expand. | Live for Manual Release for Follow Ups (did not want to automate due to clinic wf). | Allow for follow ups except Social Work follow ups based on the provider type | removed specialty excusion, added 666 to fp opt in, added exclusion to prevent SW f/ups | Addiction Medicine
Infectious Disease | MM | 3 | [9 empty] | 3 |  | FP: Live for General ID patients, not PDC or ICH. | N/A for ticket scheduling due to current operations and physician pairing in the practice. | Allow for new patients labeled at General Infectious Disease, not PDC and ICH. (PRC 533 Consults w/ general ID tag) | added prc/specialty/tag exclusion | Pediatric Infect
GPU | MM | 3 | [9 empty] | 3 |  | FP: N/A due to procedural visit exclusion. | N/A for ticket scheduling | No build change
Hematology | MM | 3 |  |  |  |  | A | [6 empty] | FP: Unable to adopt Fast Pass due to coordinated consults and follow ups within the treatment plans at this time. Interested in revisiting when this becomes possible. | Automatic Release for Follow Ups. | No build change |  | Pediatric Hematology
Ophthalmology/ Orthoptics | RH | 3 |  |  |  |  | A |  |  |  |  | 4 | 1 | FP: On, with additional logic for preventing appts at certain times | Went live with automated for 1-year follow-ups and manual release. | Meeting scheduled Tuesday |  | Pediatric Ophtha
Dialysis | MM | 3 | [11 empty] | FP: Unable to adopt Fast Pass due to coordinated consults and follow ups within the treatment plans at this time. | N/A for ticket scheduling | No build change |  | Dialysis
Allergy & Immunology | MM | 3 |  |  |  | A | A |  |  |  |  | 5 |  | FP: Going live with Consults and Follow Ups for Allergy and Immunology. Want to go live with Food Challenge, IT needs to do some additional testing to meet this request. | Live for Automatic Release for both. Also automatic release for Food Challenge orders. | Allow consults (524/532) and follow ups (651/1242) for allergy and immunology. Do not include food challenge. | removed specialty exclusion, added prc/specialty exclusion | Pediatric Allergy
Apheresis |  | 3 | [9 empty] | 1 |  | FP: Unable to adopt Fast Pass due to coordinated consults and follow ups within the treatment plans at this time. | N/A for ticket scheduling | No build change |  | Transfusion
Sports Medicine | LK | 4 |  |  |  |  | M |  |  |  |  | 11 |  | FP: Live with Consults starting next week. Difficulties to offer follow ups dues to coordinated scheduling with systems external to Epic. | Live for Manual Release for Follow Ups. Challenges operationally against automatic release. | Allow new patient consults (PRCS: 574/289/1554/1577/1562/1584/1581/1561) | removed specialty exclusion, added prc/specialty exclusion | Pediatric Sports
Nephrology | MM | 4 |  |  |  | M | A |  |  |  |  | 4 |  | Fast pass - Follow ups live, exclude kidney txp and dialysis. Arifa send list of RFV to IT to filter which visits should get offers. (Consults and follow ups) | Live for Manual Release for Referrals. Live for Automatic for Follow Ups. | Allow for follow ups and consults filtered by RFV. Waiting on list from Arifa. |  | Pediatric Nephrology
Gastroenterology | MM | 4 |  |  |  | M | A |  |  |  |  | 6 |  | FP: Live for consults and follow ups. Future potential with adding on same day/next day consults etc. Heavy cancel rate on Mondays. | Live for Manual Release for Referrals. Live for Automatic for Follow Ups. | No build change |  | Pediatric Gastro
Infusion | KR | 4 | [11 empty] | FP: Unable to adopt Fast Pass due to coordinated consults and follow ups within the treatment plans at this time. | N/A for ticket scheduling | No build change |  | Infusion Therapy
Adolescent | MM | 4 |  |  |  |  | A |  |  |  |  | 11 | 1 | FP: Live with consults and follow ups. Explore ticket scheduling. | Working on request to automate sending follow up tickets, pending Physician approval/review | Allow for visit types 671, 702, 1072, and 670. | removed specialty exclusion, added prc/specialty exclusion | Adolescent Medicine
Lead (Pediatric Environmental Health) | MM | 4 |  |  |  |  | M | [6 empty] | FP: Not live at this time due to prerequisite clinical information required for visits to be successful. Next: Review ticket scheduling opportunities | Open to implementing, need to sort out some complexity in order to explore automatic release. Live for Manual release for follow ups. | No build change
NICU Grads | MM | 4 |  |  | X | [6 empty] | 1 |  | FP: Do not feel this is necessary in NICU grads due to patient population, low volume. Some MD follow ups that would prehaps fit into a phase 2 effort with some additional logic. | N/A for ticket scheduling | No build change |  | Neonatology
Orthopaedics | LK | 5 |  |  |  |  | M |  | RAA |  |  | 14 | 2 | FP: Live with Consults starting next week. Difficulties to offer follow ups dues to coordinated scheduling with systems external to Epic. | Live for Manual Release for Follow Ups. Challenges operationally against automatic release. | Allow for consults. Must test and send list to verify potential offers before go-live with Julie, Wes, and Adrienne (PRCS: 732/1618/1620/1609/1621) | removed specialty exclusion, added prc/specialty exclusion
CCS | MM | 5 | [9 empty] | 1 |  | FP: No opportunity today. Taking patients same day. Potentially in the future as clinic becomes busier. | N/A for ticket scheduling | No build change
MEHC | MM | 5 |  |  |  |  | M |  |  |  |  | 2 |  | FP: Not live in BH (Provider request), live for new and follow ups. Next: Review how MEHC can align with their BCH counterparts. (BH) | Approved to go live with manual release in CHPCC, WEY, and MEHC primary cares) | Meeting scheduled on Thursday | Exclude MEHC Behavioral Health DEP (psych turning on)
Dentistry/Orthodontics | LK | 5 |  |  |  |  | M/A | [6 empty] | FP: Live and happy with it. Next step: Interested in exploring ticket scheduling opportunities. | Live for Manual release of Treatment Plan visits. Live for Automatic Ortho Follow Ups. Continuing to discuss automatic release. | No build change
Rheumatology | MM | 5 |  |  |  | X | A |  |  |  |  | 4 |  | FP: Live for consults and follow ups. Ticket scheduling live for follow ups. Review ambulatory referral order to find barrier to self scheduling. | Live for automatic release of Follow Ups. | No build change
ETU | KR | 5 | [9 empty] | 1 |  | FP: Unable to adopt Fast Pass due to coordinated consults and follow ups within the treatment plans at this time. | N/A for ticket scheduling | No build change
DEXA/Bone Density | MM | 5 | [11 empty] | FP: N/A due to procedural visit exclusion. | N/A for ticket scheduling | No build change
Neuropsychology (psych) | RH | 5 | [11 empty] | FP: Live for consults. | N/A for ticket scheduling | No build change
CAPE (Vent HH) | RH | 5 | [11 empty] | FP: Patient population not appropriate for Fast Pass or ticket scheduling. | N/A for ticket scheduling | No build change
CR (Crisis Response) | MM | 6 | [11 empty] | FP: Coordinating space with CHPCC and small managed group of patients. Not appropriate at this time. | N/A for ticket scheduling | No build change
Transplant | LK | 6 | [11 empty] | FP: Not appropriate based on Transplant episode coordination. Continue to monitor self service opportunities as features change. | N/A for ticket scheduling | No build change | left Tx exclusion, removed [1666] Heart TX PRC from eligible follow ups for fast pass
Heart Center (all areas) | PH | 6 |  |  |  |  | A |  |  |  |  | 12 | 1 | Follow up visits in Fast pass (not consults) (approved by KP/SA) | Live for manual release of Follow Ups. Pushing to explore automatic ticket bundling. Excited to lead the organization as an example of what is possible. Ongoing feedback from Nolan to bring additional procedures up on ticket scheduling. Includes ticket bundling - but need coordination with Cupid (for procedure tickets) | No build change
PT/OT | JG | 6 | [11 empty] | FP: Interested in seeing functionality for Initial Evals (follow ups won't work for fast pass and won't work for ticket scheduling unless parameters are available for correct gaps between appts based on order) | Interested in consult, but requires updates to decision trees to make patient facing and have not pursued. | No build change
General Surgery | LK | 6 |  |  |  | A | A |  |  |  |  | 1 |  | FP: live for consults and follow ups. | Live for automatic release of Follow Ups. | No build change
Genetics | MM | 6 |  |  |  |  | A | [6 empty] | FP: Live for consults and follow ups. | Live for automatic release of Follow Ups. | No build change
Lab | RH | 6 | [11 empty] | FP: Right now scheduling same day and next day, wouldn't hit criteria. Want to move to walk-ins only if possible, but some labs are medication timed. Live in direct scheduling. Ticket scheduling ruled out based on criteria but replicated in a way through the direct scheduling workflow. Patients are only allowed to direct schedule if they have a lab order in a specific grouper of tests. Otherwise patient must call to schedule. | N/A for ticket scheduling | No build change
Palliative Care (PACT) | MM | 6 | [9 empty] | 1 |  | FP: Patient population not appropriate for Fast Pass or ticket scheduling. | N/A for ticket scheduling | No build change
Neurology/Neurophysiology | RH | 7 |  |  |  |  | A |  |  |  |  | 7 |  | FP: live for consults and follow ups. | Live for Manual Release for Follow Ups and Consults. Automatic releasing for EEGs 5/5 - Epilepsy went live with automation of follow ups, pending remainder of specialty to give feedback | No build change
Autism Spectrum Center | RH | 7 | [11 empty] | FP: Live for consults. Follow ups are in Neurology bucket. | N/A for ticket scheduling | No build change
Neuropsychology (Neuro) | RH | 7 | [9 empty] | 6 |  | FP: Live for consults. | N/A for ticket scheduling | No build change
Pain Clinic/Interventional | RH | 7 |  |  |  |  | M |  |  |  |  | 1 |  | FP: Previously marked as live, but not currently. Follow up conversation needed. | Live for Manual Release for Follow Ups. | No build change
Pulmonary | MM | 7 |  |  |  | A | A |  |  |  |  | 1 |  | FP: Previously marked as live, but not currently. Follow up conversation needed. | Live for Automatic Release for Follow Ups and Consults | No build change
Dermatology | MM | 7 |  |  |  | M | A |  |  |  |  | 3 |  | FP: Follow ups live | Live for Manual Release for new patients. Automatic release for follow ups. | No build change
CV Surgery | PH | 7 |  |  | x | [8 empty] | FP: External second opinion process is new to Epic. Want to build trust in the workflow before explore self-service. | Follow up conversation needed. | No build change
Neurosurgery | LK | 7 | [9 empty] | 2 |  | Interested in Online Ticket Scheduling and Fast Pass (on for follow ups) but need to agree to the scope. (Operational) | Follow up conversation needed. | No build change
Total | [11 empty] | 190 | 5
Key:
Light gray - not applicable | [5 empty] | M - Manual |  |  | RAA- Request an Appt Workflow Only | [6 empty] | Other issues:
Yellow - Opportunity to improve | [5 empty] | A - Automatic / live for both Manual and Automatic release | [9 empty] | non-consult/follow-ups allowing fast pass offers (urodynamics, support staff, group | added PRCs to exclude list
Green - Satisfactory and functional
Red - Concerns / Not On
Light Green - On, but additional opportunity
Purple - In Progress
Note on I8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Hardina, Kate is this direct scheduling? It's not on for open...
Note on I13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Hardina, Kate this is not on for open scheduling....does plastics have direct scheduling (which means they are allowing f/u scheduling without orders?)
Note on I14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Hardina, Kate Wasn't this turned off after go live?
Note on I32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Hardina, Kate Wasn't this turned off after we went live due to scheduling errors?
Note on I39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Hardina, Kate Neuropsych is an intake based workflow, open scheduling would not work for this....do they have direct on?

## Status Snapshot (Archive)
Area | Wave | Analyst | Pre-Meet Documentation | Kick-off/ Scope Sign off | Build & Test 1 /Primary | Dept. Touchbase | Test 2 / Peer Test & My Chart | Dept Test & Validation Session | Dept Demo & Final Sign off | Training & Communication | Migration to PRD | Post Live Issue Resolution | Comments
Nutrition | 1 | Travis | 2024-06-26 | 2024-07-01 | 2024-07-10 |  | 2024-07-11 | 2024-07-12 | 2024-07-15 | 2024-07-18 | 2024-07-19 | 2024-07-26
Urology | 1 | Dan | 2024-06-26 | 2024-07-02 | 2024-07-10 |  | 2024-07-11 | 2024-07-12 | 2024-07-17 | 2024-07-18 | 2024-07-19 | 2024-07-26
CHPCC | 1 | Boris | 2024-06-26 | 2024-07-03 | 2024-07-18 | 2024-07-18 | 2024-07-19 | 2024-07-22 | 2024-07-23 | 2024-07-23 | 2024-07-24 | 2024-07-31
ORL | 2 | Dan | 2024-07-23 | 2024-07-30 | 2024-08-12 | 2024-08-09 | 2024-08-13 | 2024-08-14 | 2024-08-15 | 2024-08-15 | 2024-08-16 | 2024-08-23
Audiology | 2 | Dan | 2024-07-23 | 2024-07-30 | 2024-08-09 | 2024-08-09 | 2024-08-13 | 2024-08-14 | 2024-08-15 | 2024-08-15 | 2024-08-16 | 2024-08-23
Speech | 2 | Boris | 2024-07-23 | 2024-07-30 | 2024-08-07 | 2024-08-06 | 2024-08-12 | 2024-08-13 | 2024-08-14 | 2024-08-15 | 2024-08-16 | 2024-08-23
Endocrinology/GeMs/OWL | 2 | Shannon/Michelle | 2024-07-23 | 2024-07-30 | 2024-08-09 | 2024-08-06 | 2024-08-09 | 2024-08-09 | 2024-08-14 | 2024-08-15 | 2024-08-16 | 2024-08-23 | Asking when the orders will be updated to reflect the new VTs.
Gynecology | 2 | Michelle | 2024-07-23 | 2024-07-31 | 2024-08-07 | 2024-08-05 | 2024-08-07 | 2024-08-07 | 2024-08-14 | 2024-08-15 | 2024-08-16 | 2024-08-23
Behavioral Health/Psychiatry | 2 | Travis | 2024-07-23 | 2024-08-01 | 2024-08-07 | 2024-08-08 | 2024-08-12 | 2024-08-12 | 2024-08-13 | 2024-08-15 | 2024-08-16 | 2024-08-23
Plastic Surgery | 2 | Boris | 2024-07-23 | 2024-07-31 | 2024-08-07 | 2024-08-06 | 2024-08-08 | 2024-08-09 | 2024-08-13 | 2024-08-15 | 2024-08-16 | 2024-08-23
Sleep Center | 2 | Shannon | 2024-07-23 | 2024-08-02 | 2024-08-05 | 2024-08-06 | 2024-08-09 | 2024-08-09 | 2024-08-13 | 2024-08-15 | 2024-08-16 | 2024-08-23
Vaccine Clinic/Travel Clinic | 2 | Travis | 2024-07-23 | 2024-08-02 | 2024-08-06 | 2024-08-06 | 2024-08-08 | 2024-08-09 | 2024-08-13 | 2024-08-15 | 2024-08-16 | 2024-08-23
Developmental Medicine | 3 | Michelle | 2024-08-19 | 2024-08-28 | 2024-09-04 | 2024-09-04 | 2024-09-05 | 2024-09-06 | 2024-09-11 | 2024-09-12 | 2024-09-13 | 2024-09-20
ASAP | 3 | Michelle | 2024-08-19 | 2024-08-28 | 2024-09-04 | 2024-09-04 | 2024-09-05 | 2024-09-06 | 2024-09-11 | 2024-09-12 | 2024-09-13 | 2024-09-20
Infectious Disease | 3 | Travis | 2024-08-19 | 2024-08-29 | 2024-09-04 | 2024-09-04 | 2024-09-05 | 2024-09-06 | 2024-09-12 | 2024-09-12 | 2024-09-13 | 2024-09-20
GPU | 3 | Michelle | 2024-08-19 | 2024-08-29 | 2024-09-04 | 2024-09-04 | 2024-09-05 | 2024-09-06 | 2024-09-10 | 2024-09-12 | 2024-09-13 | 2024-09-20
Hematology | 3 | Travis | 2024-08-19 | 2024-08-28 | 2024-09-04 | 2024-09-04 | 2024-09-05 | 2024-09-06 | 2024-09-11 | 2024-09-12 | 2024-09-13 | 2024-09-20
Ophthalmology/ Orthoptics | 3 | Shannon | 2024-08-19 | 2024-08-30 | 2024-09-04 | 2024-09-04 | 2024-09-05 | 2024-09-06 | 2024-09-13 | 2024-09-12 | 2024-09-13 | 2024-09-20
Dialysis | 3 | Dan | 2024-08-19 | 2024-08-27 | 2024-09-04 | 2024-09-04 | 2024-09-05 | 2024-09-06 | 2024-09-09 | 2024-09-12 | 2024-09-13 | 2024-09-20
Allergy & Immunology | 3 | Boris | 2024-08-19 | 2024-08-30 | 2024-09-04 | 2024-09-04 | 2024-09-05 | 2024-09-06 | 2024-09-11 | 2024-09-12 | 2024-09-13 | 2024-09-20
Apheresis | 3 | Dan | 2024-08-19 | 2024-08-28 | 2024-09-04 | 2024-09-04 | 2024-09-05 | 2024-09-06 | 2024-09-10 | 2024-09-12 | 2024-09-13 | 2024-09-20
Sports Medicine | 4 | Boris | 2024-09-16 | 2024-09-24 | 2024-10-02 | 2024-10-02 | 2024-10-03 | 2024-10-04 | 2024-10-10 | 2024-10-10 | 2024-10-11 | 2024-10-18 | Lots of subgroup swaps, not too many new visit type requests. Meeting with Julie daily.
Nephrology | 4 | Travis | 2024-09-16 | 2024-09-23 | 2024-10-02 | 2024-10-02 | 2024-10-03 | 2024-10-04 | 2024-10-10 | 2024-10-10 | 2024-10-11 | 2024-10-18 | Large scope of RFV that didn't move from POC to PRD.
Gastroenterology | 4 | Shannon | 2024-09-16 | 2024-09-25 | 2024-10-02 | 2024-10-02 | 2024-10-03 | 2024-10-04 | 2024-10-09 | 2024-10-10 | 2024-10-11 | 2024-10-18 | Meeting almost daily - they have a lot, still scoping their triage work. Nervous but excited to try things. Online scheduling - discussing more in depth.
Infusion | 4 | Michelle | 2024-09-16 | 2024-09-23 | 2024-10-02 | 2024-10-02 | 2024-10-03 | 2024-10-04 | 2024-10-09 | 2024-10-10 | 2024-10-11 | 2024-10-18
Adolescent | 4 | Michelle | 2024-09-16 | 2024-09-26 | 2024-10-02 | 2024-10-02 | 2024-10-03 | 2024-10-04 | 2024-10-07 | 2024-10-10 | 2024-10-11 | 2024-10-18 | Finalized and agreed to a scope with Jackson today.
Lead (Pediatric Environmental Health) | 4 | Travis | 2024-09-16 | 2024-09-27 | 2024-10-02 | 2024-10-02 | 2024-10-03 | 2024-10-04 | 2024-10-10 | 2024-10-10 | 2024-10-11 | 2024-10-18 | Smaller
NICU Grads | 4 | Shannon | 2024-09-16 | 2024-09-26 | 2024-10-02 | 2024-10-02 | 2024-10-03 | 2024-10-04 | 2024-10-10 | 2024-10-10 | 2024-10-11 | 2024-10-18
Orthopaedics | 5 | Boris | 2024-10-14 | 2024-10-21 | 2024-10-24 | 2024-10-25 | 2024-10-31 | 2024-11-01 | 2024-11-04 | 2024-11-07 | 2024-11-08 | 2024-11-15
CCS (Complex Care) | 5 | Michelle | 2024-10-14 | 2024-10-24 | 2024-10-30 | 2024-10-30 | 2024-10-31 | 2024-11-01 | 2024-11-06 | 2024-11-07 | 2024-11-08 | 2024-11-15
MEHC | 5 | Shannon | 2024-10-14 | 2024-10-22 | 2024-10-30 | 2024-10-30 | 2024-10-31 | 2024-11-01 | 2024-11-06 | 2024-11-07 | 2024-11-08 | 2024-11-15
Dentistry/Orthodontics | 5 | Michelle | 2024-10-14 | 2024-10-21 | 2024-10-30 | 2024-10-30 | 2024-10-31 | 2024-11-01 | 2024-11-06 | 2024-11-07 | 2024-11-08 | 2024-11-15
Rheumatology | 5 | Travis | 2024-10-14 | 2024-10-23 | 2024-10-30 | 2024-10-30 | 2024-10-31 | 2024-11-01 | 2024-11-06 | 2024-11-07 | 2024-11-08 | 2024-11-15
ETU | 5 | Travis | 2024-10-14 | 2024-10-23 | 2024-10-30 | 2024-10-30 | 2024-10-31 | 2024-11-01 | 2024-11-06 | 2024-11-07 | 2024-11-08 | 2024-11-15 | "Scheduler App" - Double scheduling in Epic+scheduler, any future plans in higher level IT discussions
DEXA/Bone Density | 5 | Travis | 2024-10-14 | 2024-10-23 | 2024-10-30 | 2024-10-30 | 2024-10-31 | 2024-11-01 | 2024-11-06 | 2024-11-07 | 2024-11-08 | 2024-11-15
Neuropsychology (Psych) | 5 | Dan | 2024-10-14 | 2024-10-22 | 2024-10-30 | 2024-10-30 | 2024-10-31 | 2024-11-01 | 2024-11-06 | 2024-11-07 | 2024-11-08 | 2024-11-15 | Focusing on the psychiatry portion
CAPE (Vent HH) | 5 | Michelle | 2024-10-14 | 2024-10-23 | 2024-10-30 | 2024-10-30 | 2024-10-31 | 2024-11-01 | 2024-11-06 | 2024-11-07 | 2024-11-08 | 2024-11-15
CR (Crisis Response) | 6 | Shannon | 2024-11-11 | 2024-11-21 | 2024-12-04 | 2024-12-04 | 2024-12-05 | 2024-12-06 | 2024-12-10 | 2024-12-12 | 2024-12-13 | 2024-12-20 | Pretty much done. Feeling good about things.
Transplant (Kidney) | 6 | Travis | 2024-11-11 | 2024-11-18 | 2024-12-04 | 2024-12-04 | 2024-12-05 | 2024-12-06 | 2024-12-11 | 2024-12-12 | 2024-12-13 | 2024-12-20 | Doing well, fuller demo is on Thursday.
Heart Center (all areas) | 6 | Dan | 2024-11-11 | 2024-11-22 | 2024-12-04 | 2024-12-04 | 2024-12-05 | 2024-12-06 | 2024-12-12 | 2024-12-16 | 2024-12-17 | 2024-12-27 | Verify timelines
PT/OT | 6 | Travis | 2024-11-11 | 2024-11-19 | 2024-12-04 | 2024-12-04 | 2024-12-05 | 2024-12-06 | 2024-12-12 | 2024-12-12 | 2024-12-13 | 2024-12-24 | A lot of work but going well
General Surgery | 6 | Michelle | 2024-11-11 | 2024-11-20 | 2024-12-04 | 2024-12-04 | 2024-12-05 | 2024-12-06 | 2024-12-11 | 2024-12-12 | 2024-12-13 | 2024-12-20 | Stubborn but ok
Genetics | 6 | Michelle | 2024-11-11 | 2024-11-19 | 2024-12-04 | 2024-12-04 | 2024-12-05 | 2024-12-06 | 2024-12-11 | 2024-12-12 | 2024-12-13 | 2024-12-20 | Triage concerns, Shannon stepping in to help build. Scheduling Admin - out of the office, time consuming to get the info we need
Lab | 6 | Shannon | 2024-11-11 | 2024-11-20 | 2024-12-04 | 2024-12-04 | 2024-12-05 | 2024-12-06 | 2024-12-11 | 2024-12-12 | 2024-12-13 | 2024-12-20 | Happy about new one-click build.
Palliative Care (PACT) | 6 | Boris | 2024-11-11 | 2024-11-22 | 2024-12-04 | 2024-12-04 | 2024-12-05 | 2024-12-06 | 2024-12-11 | 2024-12-12 | 2024-12-13 | 2024-12-20
Neurology/Neurophysiology | 7 | Dan | 2024-12-16 | 2024-01-07 | 2024-01-16 | 2024-01-16 | 2024-01-17 | 2024-01-18 | 2024-01-21 | 2024-01-22 | 2024-01-24 | 2024-01-31 | Second kick off meeting 1/9. Looping Amb into the Neurophys
Autism Spectrum Center | 7 | Shannon | 2024-12-16 | 2024-01-08 | 2024-01-17 | 2024-01-17 | 2024-01-18 | 2024-01-19 | 2024-01-22 | 2024-01-23 | 2024-01-24 | 2024-01-31 | Medium/Complex
Neuropsychology (Neuro) | 7 | Dan | 2024-12-16 | 2024-01-08 | 2024-01-17 | 2024-01-17 | 2024-01-18 | 2024-01-19 | 2024-01-22 | 2024-01-23 | 2024-01-24 | 2024-01-31 | Focusing on the neuro portion
Pain Clinic/Interventional | 7 | Boris | 2024-12-16 | 2024-01-08 | 2024-01-17 | 2024-01-17 | 2024-01-18 | 2024-01-19 | 2024-01-22 | 2024-01-23 | 2024-01-24 | 2024-01-31 | Includes lung txp
Pulmonary | 7 | Travis | 2024-12-16 | 2024-01-07 | 2024-01-16 | 2024-01-16 | 2024-01-17 | 2024-01-18 | 2024-01-21 | 2024-01-22 | 2024-01-24 | 2024-01-31
Dermatology | 7 | Boris | 2024-12-16 | 2024-01-09 | 2024-01-18 | 2024-01-18 | 2024-01-19 | 2024-01-20 | 2024-01-22 | 2024-01-23 | 2024-01-24 | 2024-01-31 | Asking for a lot of DT changes, could be bigger than anticipating
CV Surgery | 7 | Travis | 2024-12-16 | 2024-01-07 | 2024-01-16 | 2024-01-18 | 2024-01-17 | 2024-01-18 | 2024-01-22 | 2024-01-23 | 2024-01-24 | 2024-01-31 | Want scheduling for second opinion program.
Neurosurgery | 7 | Shannon | 2024-12-16 | 2024-01-09 | 2024-01-18 | 2024-01-18 | 2024-01-19 | 2024-01-20 | 2024-01-23 | 2024-01-24 | 2024-01-24 | 2024-01-31
MFCC | Out
DFCI | TBD
DHHP | TBD
Security Subtemplate Work | TBD | [11 empty] | Wave 8
Key:
Light gray - not started
Yellow - Scheduled
Green - In Progress/On Track
Blue - Complete
Red: Concern/Off Track
Formulas:
Build & Test 1 /Primary = [Kick-off/ Scope Sign off]+9
Test 2 / Peer Test & My Chart = [Build & Test 1 /Primary]+1
Dept Test & Validation Session = [Test 2 / Peer Test & My Chart]+1
Training & Communication = [Dept Demo & Final Sign off]+1
Post Live Issue Resolution = [Migration to PRD]+7
Migration to PRD = [Training & Communication]+1
Note on D2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Date reflects "due to IT"
Note on B18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No blocks doc
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No blocks doc
Note on B27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No blocks doc
Note on A36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No blocks
Note on A38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Unsure of dep blocks based on info
Note on A39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No blocks
Note on A47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: LW Palliative Care? No blocks
Note on B49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Blocks are under the neurology department since ASC is scheduled under that DEP
Note on B50: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Same as Neurology

## Project Objectives
|  | email | meeting | Auto-scheduler works for department | Auto-scheduler works for PLP | Ticket Scheduling (Amb Ref) | Ticket Scheduling - Follow Up order | Fast Pass (Live in PRD) | Open/Direct Scheduling | Techincal Readiness for Automatic Follow up Ticket Scheduling | Notes from Column I | (PostWaveOpt) Resolved | (PostWaveOpt) Open | Status Notes | Jira Notes | PRD DEP Specialty
Area | Wave
Nutrition | 1 | S | S | [7 empty] | Visit type integtation with follow up order.(EAP Build , LQF Build, PLS Build) | 7 |  |  |  | Nutrition
Urology | 1 | S | S | [7 empty] | Visit type integtation with follow up order.(EAP Build , LQF Build, PLS Build) | 16 | 6 |  |  | Pediatric Urology
CHPCC | 1 | S | S | [7 empty] | Ticket Scheduling doesn't make as much sense as Direct Scheduling | 9 |  | +5 |  | Primary Care
ORL | 2 | S | S | [7 empty] | Visit type integtation with follow up order.(EAP Build and LQF Build) | 13 | 7 | +7 solved | (count is actually 3 missing wave2 on one item) | Pediatric Oto
Audiology | 2 | S | S | [7 empty] | Auto Search is functioning based on follow up order, ticket scheduling not enabled on EAP | 5 | 2 | Appointments available, not getting used. (Need someone to look at these) | (count is actually 3 missing wave2 on one item) | Pediatric Audiology
Speech | 2 | S | S | [7 empty] | Auto Search is functioning based on follow up order, ticket scheduling not enabled on EAP | 1 |  |  |  | Speech
Endocrinology/GeMs/OWL | 2 | S | S | [7 empty] | Visit type integtation with follow up order.(EAP Build , LQF Build, PLS Build) | 4 | 2 |  |  | Pediatric Endo
Gynecology | 2 | S | S | [7 empty] | Auto Search is functioning based on follow up order, ticket scheduling not enabled on EAP | 2 |  |  |  | Gynecology
Behavioral Health/Psychiatry | 2 | S | S | [7 empty] | Auto Search is functioning based on follow up order, ticket scheduling not enabled on EAP |  |  | Not appropriate to self schedule |  | Pediatric Psych
Plastic Surgery | 2 | S | S | [7 empty] | Auto Search is functioning based on follow up order, ticket scheduling not enabled on EAP | 3 | 1 |  |  | Pediatric Plastic
Sleep Center | 2 | S | S | [7 empty] | Visit type integtation with follow up order.(EAP Build , LQF Build, PLS Build) | 2 |  |  |  | Sleep Medicine
Vaccine Clinic/Travel Clinic | 2 | S | S | [7 empty] | Ticket Scheduling doesn't make as much sense , they dont have a backlog | 1 |  |  |  | Family Medicine
Developmental Medicine | 3 | S | S | [7 empty] | Auto Search is functioning based on follow up order, ticket scheduling not enabled on EAP | 1 |  | Approved for ticket scheduling only |  | Pediatric Develop
ASAP | 3 | S | S | [7 empty] | Auto Search is functioning based on follow up order, ticket scheduling not enabled on EAP |  |  | Approved for ticket scheduling only |  | Addiction Medicine
Infectious Disease | 3 | S | S | [7 empty] | Auto Search is functioning based on follow up order, ticket scheduling not enabled on EAP | 1 | 1 | Approved for ticket scheduling only (Dan looking at 2 tickets) |  | Pediatric Infect
GPU | 3 | S | P | [7 empty] | They don't have follow up order scheduling, however their other EAPS may be a good canidate | 2 | 1
Hematology | 3 | S | S | [7 empty] | Auto Search is functioning based on follow up order, they currently use manual |  |  | Significant improvement in lead times from Aug to Sept, Approved for ticket scheduling only |  | Pediatric Hematology
Ophthalmology/ Orthoptics | 3 | S | S | [7 empty] | Auto Search is functioning based on follow up order, ticket scheduling not enabled on EAP |  | 6 | Pending order sign off that will help the PLP |  | Pediatric Ophtha
Dialysis | 3 | N/A | N/A | [7 empty] | No follow up order |  |  | Not appropriate to self schedule |  | Dialysis
Allergy & Immunology | 3 | S | S | [7 empty] | Auto Search is functioning based on follow up order, they currently use manual | 2 | 4 |  |  | Pediatric Allergy
Apheresis | 3 | N/A | N/A | [7 empty] | No follow up order |  |  | Not appropriate to self schedule |  | Transfusion
Sports Medicine | 4 | S | S | [7 empty] | Auto Search is functioning based on follow up order, ticket scheduling not enabled on EAP | 7 | 2 | Self scheduling live, some follow up scheduling workflow questions. |  | Pediatric Sports
Nephrology | 4 | S | S | [7 empty] | Auto Search is functioning based on follow up order, ticket scheduling not enabled on EAP | 4 |  | Self scheduling live for specific follow ups |  | Pediatric Nephrology
Gastroenterology | 4 | S | S | [7 empty] | Auto Search is functioning based on follow up order, they currently use manual |  | 3 |  |  | Pediatric Gastro
Infusion | 4 | N/A | N/A | [7 empty] | No follow up order |  |  | Not appropriate to self schedule |  | Infusion Therapy
Adolescent | 4 | S | S | [7 empty] | Auto Search is functioning based on follow up order, they currently use manual | 9 | 2 | Self-scheduling follow ups allowed |  | Adolescent Medicine
Lead (Pediatric Environmental Health) | 4 | S | S | [7 empty] | Auto Search is functioning based on follow up order, they currently use manual
NICU Grads | 4 | N/A | N/A | [7 empty] | They don't have follow up order scheduling, however their other EAPS may be a good canidate |  | 1 |  |  | Neonatology
Orthopaedics | 5 | S | S | [7 empty] | Auto Search is functioning based on follow up order, ticket scheduling not enabled on EAP |  | 3
CCS | 5 | N/A | N/A | [7 empty] | Auto Search is functioning based on follow up order, ticket scheduling not enabled on EAP
MEHC | 5 | S | S | [7 empty] | Auto Search is functioning based on follow up order, ticket scheduling not enabled on EAP |  |  | Primary care yes. Propose turning on for specialties.
Dentistry/Orthodontics | 5 | S | S | [7 empty] | Auto Search is functioning based on follow up order, they currently use manual |  |  | Orthodontics in a better spot than Dentistry
Rheumatology | 5 | S | N/A | [7 empty] | Auto Search is functioning based on follow up order, they currently use manual | 1 | 2
ETU | 5 | N/A | N/A | [7 empty] | No follow up order |  |  | Not appropriate to self schedule
DEXA/Bone Density | 5 | N/A | N/A | [7 empty] | No follow up order |  |  | Not appropriate to self schedule
Neuropsychology | 5 | N/A | N/A | [7 empty] | Neuropsych schedules 2-3 evaluation appointments and 1 feedback session together. Patients get results at feedback, ending their specialty care.
CAPE (Vent HH) | 5 | N/A | N/A | [7 empty] | Auto Search is functioning based on follow up order, ticket scheduling not enabled on EAP
CR (Crisis Response) | 6 | N/A | N/A | [7 empty] | No follow up order
Transplant | 6 | N/A | N/A | [7 empty] | No follow up order
Heart Center (all areas) | 6 | S | S | [7 empty] | Auto Search is functioning based on follow up order, they currently use manual. Intrested in auto and auto ticket bundling (Gold Star item)
PT/OT | 6 | S | S | [7 empty] | Visit type integtation with follow up order.(EAP Build , LQF Build, PLS Build)
General Surgery | 6 | S | S | [7 empty] | Visit type integtation with follow up order.(EAP Build , LQF Build, PLS Build)
Genetics | 6 | S | S |  | Returns only | [5 empty] | Auto Search is functioning based on follow up order, they currently use manual
Lab | 6 | N/A | N/A | [7 empty] | No follow up order
Neurology/Neurophysiology | 7 | [9 empty] | Auto Search is functioning based on follow up order, they currently use manual
Autism Spectrum Center | 7 | N/A | N/A |  | Returns only | [5 empty] | ASC schedules 2-3 evaluation appointments and 1 feedback session together. Patients get results at feedback, ending their specialty care.
Pain Clinic/Interventional | 7 | [9 empty] | Visit type integtation with follow up order.(EAP Build , LQF Build, PLS Build)
Pulmonary | 7 | [9 empty] | Auto Search is functioning based on follow up order, they currently use manual. Ticket scheduling live 2/19/25
Dermatology | 7 | [9 empty] | Auto Search is functioning based on follow up order, they currently use manual
MFCC | 7 | [9 empty] | Visit type integtation with follow up order.(EAP Build , LQF Build, PLS Build)
Neurosurgery | 7 | [9 empty] | Visit type integtation with follow up order.(EAP Build , LQF Build, PLS Build)
Palliative Care (PACT) | 7 | N/A | N/A
DFCI | TBD | N/A | N/A
Multidisciplinary | N/A | N/A | N/A | [10 empty] | Fast pass appropriate?
Total | [11 empty] | 90 | 43
Key:
Light gray - not applicable
Yellow - Opportunity to improve
Green - Satisfactory and functional
Red: Concerns
Definitions:
1. Direct Scheduling
o MyChart's primary form of post-login online scheduling, allowing patients to select a location, provider, and time that works best for them. When you hear "MyChart Scheduling", you can likely safely assume that is in reference to direct scheduling.
2. Open Scheduling
o Allows patients who are new to an organization to view open time slots and schedule appointments without a MyChart account. Existing patients can also use Open Scheduling to schedule appointments with clinicians who might not otherwise be available to them through MyChart.
3. Ticket Scheduling
o Orders initiated by an organization that are sent to MyChart for a patient to schedule on their own. These appointments might not normally be available to schedule using standard direct or open scheduling

## Specialty List
Grouping/Specialty | Wave
Neurology/Neurophysiology |  | Nutrition
Urology | Wave 1 | Pediatric Urology
Nutrition | Wave 1 | Primary Care
Heart Center (all areas) |  | Pediatric Oto
ORL/Audiology/Speech |  | Pediatric Audiology
Gastroenterology |  | Speech
MEHC |  | Pediatric Endo
Developmental Medicine |  | Gynecology
Pain Clinic/Interventional |  | Pediatric Psych
Infectious Disease |  | Pediatric Plastic
CHPCC | Wave 1 | Sleep Medicine
GPU |  | Family Medicine
Infusion |  | Pediatric Develop
Orthopaedics/Sports |  | Addiction Medicine
Endocrinology/GeMs/OWL |  | Pediatric Infect
PT/OT |  | Pediatric Hematology
Allergy & Immunology |  | Pediatric Ophtha
Hematology |  | Dialysis
Behavioral Health/Psychiatry |  | Pediatric Allergy
Ophthalmology/ Orthoptics |  | Transfusion
Adolescent |  | Pediatric Sports
Dentistry/Orthodontics |  | Pediatric Nephrology
General Surgery |  | Pediatric Gastro
Pulmonary |  | Infusion Therapy
Nephrology |  | Adolescent Medicine
Rheumatology
Genetics
Apheresis
Autism Spectrum Center
ETU
ASAP/LEAD/CR
Dermatology
Transplant
MFCC
Gynecology
Plastic Surgery
Sleep Center & Epilepsy
CAPE (Vent HH)
Palliative Care (PACT)
DEXA/Bone Density
Dialysis
NICU Grads
Social Work
Lab
Neurosurgery
Vaccine Clinic/ Transplant

## Task Ownership (Archive) (hidden)
Task | BCH PM | Pt Access Analyst | Epic Lead | Operational Readiness | Operational Sponsors | EAD | Template Manager(s) | MyChart analyst | Physician Champion
Project Planning
Create education materials for block usage and template build overview |  | Support | Owner
Identify key metrics that measure the success of the optimization project
Confirm template manager, EAD, and physician champion for each specialty |  |  |  | Owner | Support
Confirm specialty grouping mapping for every schedulable Epic DEP |  |  |  | Owner | Support
Confirm specialty grouping per wave |  |  |  | Owner | Support
Pre-Work
Ensure EAD and template manager understand blocks/tags/visit types |  |  | Support | Owner
Compile list of known Jira tickets (operations) | [5 empty] | Owner | Support
Compile list of known Jira tickets (IT) | Owner
Identify blocks in use for each DEP/Specialty |  |  | Owner
Review blocks and make recommendation for keep/remove based on visit type outcomes in GPS |  | Owner | Support
Pull list of tickets submitted by specialty-review for break/fix vs optimization | Owner | Support
Prepare Department Prep package for distribution | Owner
Identify operational leads and template managers per specialty grouping, ensure they have time to dedicate to this optimization wave |  |  |  | Owner | Support | Support
Ensure EAD and template manager are adhering to guiding principles in their use of blocks and open scheduling |  |  |  | Support | Owner
Send outlook invitations for that specialties pre-work, first meeting, close out meeting, and stabilization meeting
Identify the Epic DEPs included within each specialty grouping | Owner | Support |  | Support
Meeting 1
Conduct first meetings with department |  |  | Owner
Review of recommended plan from BCH IT (Epic led) --Proposed block and template changes --Proposed GPTS/visit type changes NOTE: The department should already have an understanding of blocks and appropriate block usage per BCH guidelines |  | Support | Owner
Finalize scope based on priority for the department of optimization items for the specialty group | Owner |  |  |  | Support
Build (weeks 2-3)
Update all templates with appropriate tags and removing unnecssary blocks |  | Owner
Update decision trees to drive to right visit type/tag combo |  | Owner
Complete build on scoped priority optimization items |  | Owner
Configure allowed blocks for those departments to limit what can be used |  | Owner
Test (weeks 3-4)
QA through peer review/2nd testing |  | Owner
Conduct validation session with template builder to reproduce most impactful scheduling scenarios in REL to ensure accuracy |  | Owner | Support
Departmental leads develop communication plan on what's impacting their departmental administrative and clinical staff understand the impact |  |  |  | Support |  | Owner
Department review and sign-off (week 4)
Review adherence to the agreed upon plan |  | Owner
Small demo what major changes occurred |  | Owner
Review support expectations "post-live" -Timeline for specific resources -Jira ticket expectations | Owner
Go-live planning and timeline of new templates and decision tree into PRD | Owner
Departmental leads communicate to their department what changes have occurred so entire administrative and clinical staff understand the impact |  |  |  | Support |  | Owner
Post-live governance
Use Epic reports that monitor ongoing compliance to the scheduling guiding principles and key metrics of scheduling optimization success

## Fast Pass Plan (Archive) (hidden)
|  |  |  | Auto-scheduler works for PLP | Ticket Scheduling (Amb Ref | Ticket Scheduling - Follow Up order |  | Open/Direct Scheduling |  |  |  | PRD DEP Specialty
Area | Wave | Analyst Lead | Auto-scheduler works for department |  |  |  | Fast Pass (Live in PRD) |  | Conversation happened? | Reason Not live? (analyst feedback) | Go-Live Date
PT/OT | 6 | Travis | [6 empty] | Yes | Won't have follow ups on FastPass unless they can only move the last appt in a series to the new time. Discussing Initial Evals | 2024-12-13 | Nutrition
ORL | 2 | Dan | [6 empty] | yes | Ran out of time with initial scope | 2024-12-20 | Pediatric Urology
Audiology | 2 | Dan | [6 empty] | yes | Ran out of time with initial scope | 2024-12-20 | Primary Care
Speech | 2 | Boris | [6 empty] | Yes | Trust in the system | 2024-12-20 | Pediatric Oto
Endocrinology/GeMs/OWL | 2 | Shannon/Michelle | [6 empty] | Yes | Ran out of time with initial scope | 2024-12-20 | Pediatric Audiology
Gynecology | 2 | Michelle | [6 empty] | Yes | Ran out of time with initial scope | 2024-12-20 | Speech
Behavioral Health/Psychiatry | 2 | Travis | [6 empty] | Yes | Ran out of time to show how this would work with update workflow | 2024-12-20 | Pediatric Endo
Plastic Surgery | 2 | Boris | [6 empty] | Yes | Trust in the system | 2024-12-20 | Gynecology
Sleep Center | 2 | Shannon | [6 empty] | Yes | Did not want for sleep studies. Might have opportunities in consults | 2024-12-20 | Pediatric Psych
Vaccine Clinic/Travel Clinic | 2 | Travis | [6 empty] | Yes | Not appropriate, they mainly schedule same day | 2024-12-20 | Pediatric Plastic
ASAP | 3 | Michelle | [6 empty] | Yes | Was not using in Legacy* (will confirm) and did not want visits to move up. | 2025-01-03 | Sleep Medicine
Infectious Disease | 3 | Travis | [6 empty] | Yes | Didn't turn on due to time. Would be worth asking as they may have interest now that their scheduling is working | 2025-01-03 | Family Medicine
GPU | 3 | Michelle | [6 empty] | Yes | Concerns about moving up procedures and the prior auth implications | 2025-01-03 | Pediatric Develop
Hematology | 3 | Travis | [6 empty] | Yes | Trust in the system | 2025-01-03 | Addiction Medicine
Allergy & Immunology | 3 | Boris | [6 empty] | Yes | Trust in the system | 2025-01-03 | Pediatric Infect
Sports Medicine | 4 | Boris | [6 empty] | Yes | Trust in the system | 2025-01-10
Nephrology | 4 | Travis | [6 empty] | Yes | Ran out of time due to large decision tree needs. | 2025-01-10 | Pediatric Hematology
Adolescent | 4 | Michelle | [6 empty] | No |  | 2025-01-10 | Pediatric Ophtha
Lead (Pediatric Environmental Health) | 4 | Travis | [6 empty] | No | I don't recall having the conversation with them and didn't find any notes about it | 2025-01-10 | Dialysis
Orthopaedics | 5 | Boris | [6 empty] | Yes | Trust in the system | 2025-01-10 | Pediatric Allergy
ETU | 5 | Travis | [6 empty] | Yes | Specific research appointments. Not appropriate to move automatically | 2025-01-10 | Transfusion
Neurology/Neurophysiology | 7 | Dan | [6 empty] | No | Upcoming | 2025-01-24 | Pediatric Sports
Autism Spectrum Center | 7 | Michelle |  | Returns only |  |  |  |  | No | Upcoming | 2025-01-24 | Pediatric Nephrology
Neuropsychology (Neuro) | 7 | Dan | [6 empty] | No | Upcoming | 2025-01-24 | Pediatric Gastro
Pain Clinic/Interventional | 7 | Boris | [6 empty] | No | Upcoming | 2025-01-24 | Infusion Therapy
Pulmonary | 7 | Travis | [6 empty] | No | Upcoming | 2025-01-24 | Adolescent Medicine
Dermatology | 7 | Shannon | [6 empty] | No | Upcoming | 2025-01-24
CV Surgery | 7 | Boris | [6 empty] | No | Upcoming | 2025-01-24 | Neonatology
Neurosurgery | 7 | Michelle | [6 empty] | No | Upcoming | 2025-01-24
Ophthalmology/ Orthoptics | 3 | Shannon | [6 empty] | Yes | In Progress | N/A
Transplant | 6 | Travis | [6 empty] | No | Providers and Admin indicated not appropriate due to tightly managed schedule by nurse practiioners | N/A
Heart Center (all areas) | 6 | Dan | [6 empty] | Yes | In Progress | N/A
General Surgery | 6 | Michelle | [6 empty] | Yes | In Progress | N/A
Genetics | 6 | Michelle |  | Returns only |  |  |  |  | No | In Progress | N/A
Infusion | 4 | Michelle | [6 empty] | Yes | Series visits and controlled frequencies | N/A
DEXA/Bone Density | 5 | Travis | [6 empty] | No | Specialty was identified as not appropriate for wave and we didn't discuss Fastpass as a result | N/A
Nutrition | 1 | Travis | [6 empty] | Yes | Live | N/A
Urology | 1 | Dan | [6 empty] | Yes | Live | N/A
CHPCC | 1 | Boris | [6 empty] | Yes | Live | N/A
Developmental Medicine | 3 | Michelle | [6 empty] | Yes | Live | N/A
Dialysis | 3 | Dan | [6 empty] | Yes | Series visits and controlled frequencies | N/A
Apheresis | 3 | Dan | [6 empty] | Yes | Series visits and controlled frequencies | N/A
Gastroenterology | 4 | Shannon | [6 empty] | Yes | Live | N/A
NICU Grads | 4 | Shannon | [6 empty] | Yes | Very specific spacing between visits and approval process. | N/A
CCS | 5 | Dan | [6 empty] | Yes | Same and Next Day appointments as it is. Did not make sense to offer FastPass when patient is already coming in that day. | N/A
MEHC | 5 | Shannon | [6 empty] | Yes | Live | N/A
Dentistry/Orthodontics | 5 | Michelle | [6 empty] | Yes | Live | N/A
Rheumatology | 5 | Travis | [6 empty] | Yes | Live | N/A
Neuropsychology | 5 | Dan | [6 empty] | Yes | Panel visits not supported by Fast Pass | N/A
CAPE (Vent HH) | 5 | Michelle | [6 empty] | Yes | Not appropriate to move up. Controlled by a coordinator | N/A
Lab | 6 | Shannon | [6 empty] | Yes | Same and Next Day appointments as it is. Did not make sense to offer FastPass when patient is already coming in that day. | N/A
CR (Crisis Response) | 6 | Shannon | [6 empty] | Yes | Not appropriate to move up. Controlled by a coordinator. | N/A
Palliative Care (PACT) | 6 | Boris | [6 empty] | Yes | All scheduling facilitated by the department. Including moving up appointments. | N/A
Note on A26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Unsure of dep blocks based on info
Fast Pass go-live check list via email to DEP contact:
- Overview of guardrails (IT)
- Valid approved exceptions (managed by Ops leads)
- Dictated go-live date