## Clean_Data
Unnamed_0 | WAVE_1 | CHPCC_Boris | Urology_Dan | Nutrition_Boris | WAVE_2 | ORL_Dan | Audiology_Dan | Speech_Boris | EndocrinologyGeMsOWL_Shannon | Gynecology_Shannon | Behavioral_HealthPsychiatry_Travis | Plastic_Surgery_Dan | Sleep_Center_Shannon | Vaccine_ClinicTravel_Clinic_Travis | Group | Priority_Score | Record_ID
Update decision trees to drive to right visit type/tag combo | [14 empty] | Update all templates with appropriate tags and removing unnecssary blocks | 50 | 1
Complete build on scoped priority optimization items | [14 empty] | Update decision trees to drive to right visit type/tag combo | 50 | 2
Configure allowed blocks for those departments to limit what can be used | [14 empty] | Complete build on scoped priority optimization items | 50 | 3
Test (weeks 3-4) | 7/15-7/26 |  |  |  | 8/19-8/30 | [9 empty] | Complete build on scoped priority optimization items | 50 | 4
QA through peer review/2nd testing (including MyChart) | [14 empty] | Complete build on scoped priority optimization items | 50 | 5
Conduct validation session with template builder to reproduce most impactful scheduling scenarios in REL to ensure accuracy | [14 empty] | QA through peer review/2nd testing (including MyChart) | 50 | 6
Departmental leads develop communication plan on what's impacting their departmental administrative and clinical staff understand the impact | [14 empty] | Conduct validation session with template builder to reproduce most impactful scheduling scenarios in REL to ensure accuracy | 50 | 7
Department review and sign-off (week 4) | 7/22-7/26 |  |  |  | 8/26-8/30 | [9 empty] | Conduct validation session with template builder to reproduce most impactful scheduling scenarios in REL to ensure accuracy | 50 | 8
Review adherence to the agreed upon plan | [14 empty] | Conduct validation session with template builder to reproduce most impactful scheduling scenarios in REL to ensure accuracy | 50 | 9
Small demo what major changes occurred | [14 empty] | Review adherence to the agreed upon plan | 50 | 10
Review support expectations "post-live" -Timeline for specific resources -Jira ticket expectations | [14 empty] | Small demo what major changes occurred | 50 | 11
Go-live planning and timeline of new templates and decision tree into PRD | [14 empty] | Review support expectations "post-live" -Timeline for specific resources -Jira ticket expectations | 50 | 12
Departmental leads communicate to their department what changes have occurred so entire administrative and clinical staff understand the impact | [14 empty] | Go-live planning and timeline of new templates and decision tree into PRD | 50 | 13